## Read me
Project tracker with Gantt
How to use this template
What this does
Tracks tasks, owners, dates and progress, and draws a Gantt chart from those dates without a single manual bar.
Using it
1. Set the chart start date in the cream cell B3 on the Tasks sheet. The timeline runs from there.
2. Enter each task with an owner, a start date and a duration in days.
3. End date, Status and the chart bars all calculate themselves.
4. Update the Progress column as work proceeds.
How the chart works
There are no shapes and nothing is drawn. Each timeline cell carries a conditional formatting rule that fills it when its date falls between the task start and end. Change a date and the chart redraws instantly.
Completed tasks fill dark green, work in progress fills light green, and weekends are shaded so the working week stays readable.
Extending the timeline
The timeline covers 42 days. Move the window by changing the start date, or widen it by copying the last timeline column to the right.
Blue text on a cream background marks a cell you fill in. Black text is calculated — typing over one replaces the formula. Green shading is a heading or a total. This is the standard financial-modelling convention.

## Tasks
Project tracker
Dates drive the chart. Nothing is drawn by hand.
Chart starts | 2026-01-05
# | Task | Owner | Start | Days | End | Progress | Status
1 | Scope and requirements | Adams | 2026-01-05 | 4 |  | 100%
2 | Data audit | Brennan | 2026-01-09 | 3 |  | 100%
3 | Build data model | Adams | 2026-01-12 | 6 |  | 60%
4 | Reporting layer | Raman | 2026-01-18 | 5 |  | 20%
5 | User testing | Okafor | 2026-01-23 | 4 |  | 0%
6 | Fixes and polish | Adams | 2026-01-27 | 3 |  | 0%
7 | Training and handover | Raman | 2026-01-30 | 2 |  | 0%

## Summary
Project summary
Everything here reads from the Tasks sheet
Measure | Value | Notes
Tasks total |  | Rows with a task name
Done |  | Progress at 100%
In progress
Not started
Late |  | Started before today with no progress
Overall progress |  | Average of the progress column
Earliest start
Latest finish
Calendar days
Working days |  | Excludes weekends